## Sheet1
Manpower Statistics Report on the Development of the Cargo Delivery Program
Type | Man-hour spent |  |  | Milestone | Man-hour spent
Project Management | 10.5 |  |  | 1 | 3.25
Planning | 9 |  |  | 2 | 24.25
Analysis | 12 |  |  | 3 | 40.25
Design | 8.5 |  |  | 4 | 42.25
Implementation | 31 |  |  | 5 | 50.25
Testing | 103.5 |  |  | 6 | 14.25
Total | 174.5 |  |  | Total | 174.5
Milestone | Task | Type | Man-hour spent
1 | Distribute workload | Project Management | 0.25
1 | Prepare Team Contract | Project Management | 1
1 | Set up Git repository | Project Management | 0.5
1 | Set up Jira Project | Project Management | 0.5
1 | Prepare Scrum Report | Project Management | 1
2 | Distribute workload | Project Management | 0.25
2 | Prepare the test plan | Planning | 9
2 | Understand the business requirements | Analysis | 6
2 | Understand the existing system design | Analysis | 6
2 | Design the data structures | Design | 1
2 | Implement the data structures | Implementation | 1
2 | Prepare Scrum Report | Project Management | 1
3 | Distribute workload | Project Management | 0.25
3 | Prepare function specifications | Design | 7.5
3 | Prepare blackbox test documents | Testing | 12
3 | Write blackbox test codes | Testing | 1
3 | Implement individual functions | Implementation | 18
3 | Prepare function-test matrix | Testing | 0.5
3 | Prepare Scrum Report | Project Management | 1
4 | Distribute workload | Project Management | 0.25
4 | Set up test environment | Testing | 3
4 | Prepare whitebox test documents | Testing | 7.5
4 | Implement and execute blackbox and whitebox tests | Testing | 18
4 | Debugging | Testing | 12
4 | Update function-text matrix | Testing | 0.5
4 | Prepare Scrum Report | Project Management | 1
5 | Distribute workload | Project Management | 0.25
5 | Implement the main function | Implementation | 12
5 | Prepare integration test documents | Testing | 12
5 | Implement and execute integration tests | Testing | 12
5 | Debugging | Testing | 12
5 | Conduct acceptance test | Testing | 0.5
5 | Update function-text matrix | Testing | 0.5
5 | Prepare Scrum Report | Project Management | 1
6 | Distribute workload | Project Management | 0.25
6 | Confirm acceptance test | Testing | 0.5
6 | Update function-text matrix | Testing | 0.5
6 | Prepare test reports | Testing | 11
6 | Prepare manpower statistics report | Project Management | 1
6 | Prepare Scrum Report | Project Management | 1
Total |  |  | 174.5